## Week
TSPi Week Summary - Form WEEK
Name | Rokas Jaruševičius |  | Date | 04/13/2018
Team | Gryffindor |  | Instructor | Saulius Ragaišis
Week | 1 |  | Cycle | 1
Weekly Data |  |  | Plan | Actual
Project hours for this week |  |  | 40 | 42.5
Project hours this cycle to date |  |  | 76 | 66.5
Earned value for this week |  |  | 40 | 40
Earned value this cycle to date |  |  | 40 | 40
Total hours for the tasks completed this phase to date |  |  | 40 | 42.5
Team Member Weekly Data | Team Plan Hours | Team Actual Hours | Team Plan Value | Team Earned Value
Team Leader | 8 | 9.5 | 8 | 8
Development Manager | 8 | 8.5 | 8 | 8
Planning Manager | 8 | 8 | 8 | 8
Quality/Process Manager | 8 | 9 | 8 | 8
Support Manager | 8 | 7.5 | 8 | 8
Totals | 40 | 42.5 | 40 | 40
Development Tasks Completed | Plan Hours | Actual Hours | Earned Value | Plan Week
Registracija | 5 | 4.5 | 5 | 5
Authentifikacija | 5 | 5.5 | 5 | 5
Autorizacija pagal roles | 5 | 3 | 5 | 5
Userių paskyrų trinimas | 3 | 3 | 3 | 3
Userių promotion/demotion | 4 | 2.5 | 4 | 4
Prekių peržiūra, dėjimas į krepšelį | 4 | 5.5 | 4 | 4
Krepšelio realizacija | 6 | 7.5 | 6 | 6
Testavimas | 3 | 2.5 | 3 | 3
Debbuging | 5 | 8.5 | 5 | 5
| 40 | 42.5 | 40 | 40