## Week
TSPi Week Summary - Form WEEK
Name | Rokas Jaruševičius |  | Date | 05/18/2018
Team | Gryffindor |  | Instructor | Saulius Ragaišis
Week | 2 |  | Cycle | 3
Weekly Data |  |  | Plan | Actual
Project hours for this week |  |  | 43 | 43
Project hours this cycle to date |  |  | 86 | 83
Earned value for this week |  |  | 43 | 43
Earned value this cycle to date |  |  | 86 | 83
Total hours for the tasks completed this phase to date |  |  | 86 | 83
Team Member Weekly Data | Team Plan Hours | Team Actual Hours | Team Plan Value | Team Earned Value
Team Leader | 7 | 6.5 | 7 | 7
Development Manager | 8 | 8.5 | 8 | 8
Planning Manager | 8 | 8 | 8 | 8
Quality/Process Manager | 10 | 12.5 | 10 | 10
Support Manager | 10 | 11 | 10 | 10
Totals | 43 | 46.5 | 43 | 43
Development Tasks Completed | Plan Hours | Actual Hours | Earned Value | Plan Week
CC info saugojimas anketoje, šifravimas | 3 | 3 | 3 | 3
Excel import/export | 15 | 18 | 15 | 15
Layerių atskyrimas | 6 | 5.5 | 6 | 6
E-mail servisas | 6 | 5 | 6 | 6
Refactorintas kodas | 5 | 4.5 | 5 | 5
Testavimas | 3 | 3 | 3 | 3
Debugginimas | 5 | 7.5 | 5 | 5
| 43 | 46.5 | 43 | 43