## Week
TSPi Week Summary - Form WEEK
Name | Rokas Jaruševičius |  | Date | 04/20/2018
Team | Gryffindor |  | Instructor | Saulius Ragaišis
Week | 1 |  | Cycle | 2
Weekly Data |  |  | Plan | Actual
Project hours for this week |  |  | 40 | 37.5
Project hours this cycle to date |  |  | 40 | 37.5
Earned value for this week |  |  | 40 | 40
Earned value this cycle to date |  |  | 40 | 40
Total hours for the tasks completed this phase to date |  |  | 40 | 37.5
Team Member Weekly Data | Team Plan Hours | Team Actual Hours | Team Plan Value | Team Earned Value
Team Leader | 8 | 9.5 | 8 | 8
Development Manager | 8 | 9 | 8 | 8
Planning Manager | 8 | 5.5 | 8 | 8
Quality/Process Manager | 8 | 8 | 8 | 8
Support Manager | 8 | 5.5 | 8 | 8
Totals | 40 | 37.5 | 40 | 40
Development Tasks Completed | Plan Hours | Actual Hours | Earned Value | Plan Week
Laiko suplanavimas | 2 | 1.1 | 2 | 2
Strategijos papildymas | 2 | 0.5 | 2 | 2
Naujų atsiradusių rizikų identifikavimas | 2 | 0.5 | 2 | 2
Database modelio pakoregavimas | 2 | 1 | 2 | 2
Koncepcinio modelio koregavimas | 3 | 2 | 3 | 3
Testavimo plano sukūrimas antram ciklui | 2 | 1 | 2 | 2
Navigacijos realizavimas | 5 | 6.5 | 5 | 5
Product detailed description realizavimas | 5 | 2.5 | 5 | 5
Asmeniniai produktų puslapiai | 5 | 4 | 5 | 5
Administravimo sąsajos f-jų papildymas | 6 | 10.5 | 6 | 6
Unit testai | 3 | 1.5 | 3 | 3
Debugginimas | 9 | 8.5 | 9 | 9
| 40 | 37.5 | 40 | 40