## Week
TSPi Week Summary - Form WEEK
Name | Rokas Jaruševičius |  |  |  | Date |  | 04/13/2018
Team | Gryffindor |  |  |  | Instructor |  | Saulius Ragaišis
Week | 2 |  |  |  | Cycle |  | 1
Weekly Data |  |  |  |  | Plan |  | Actual
Project hours for this week |  |  |  |  | 30 |  | 10
Project hours this cycle to date |  |  |  |  | 66 |  | 34
Earned value for this week |  |  |  |  | 24 |  | 25
Earned value this cycle to date |  |  |  |  | 24 |  | 25
Total hours for the tasks completed this phase to date |  |  |  |  | 66 |  | 34
Team Member Weekly Data | Team Plan Hours |  | Team Actual Hours |  | Team Plan Value |  | Team Earned Value
Team Leader
Development Manager | 10 |  | 10 |  | 10 |  | 11
Planning Manager | 8 |  | 5 |  | 8 |  | 8
Quality/Process Manager
Support Manager | 7 |  | 4 |  | 6 |  | 6
0
Totals | 25 | 0 | 19 | 0 | 24 | 0 | 25
Development Tasks Completed | Plan Hours |  | Actual Hours |  | Earned Value |  | Plan Week
Krepšelio funkcionalumo įgyvendinimas | 10 |  | 10 |  | 10 |  | 10
Duomenų bazės koregavimas | 1 |  | 2 |  | ?????? Kiek? -1? XD |  | 0, nes neplanuota xD
Produkto aprašymo punktų atvaizdavimas | 3 |  | 3 |  | 3 |  | 3
Produkto aprašymo punktų pridėjimas bei trynimas | 7 |  | 5 |  | 7 |  | 7