## Week
TSPi Week Summary - Form WEEK
Name | Denis Semionov |  |  | Date | 2018-04-05
Team | Gryffindor |  |  | Instructor | Saulius Ragaišis
Week | 3 |  |  | Cycle | 2
Weekly Data |  |  |  | Plan | Actual
Project hours for this week |  |  |  | 40 | 48
Project hours this cycle to date |  |  |  | 120 | 130.5
Earned value for this week |  |  |  | 40 | 48
Earned value this cycle to date |  |  |  | 120 | 130.5
Total hours for the tasks completed this phase to date |  |  |  | 120 | 130.5
Team Member Weekly Data | Team Plan Hours | Team Actual Hours |  | Team Plan Value | Team Earned Value
Team Leader | 8 | 12 |  | 8 | 12
Development Manager | 8 | 12 |  | 8 | 12
Planning Manager | 8 | 8 |  | 8 | 8
Quality/Process Manager | 8 | 8 |  | 8 | 8
Support Manager | 8 | 8 |  | 8 | 8
Totals | 40 | 48 |  | 40 | 48
Development Tasks Completed | Plan Hours | Actual Hours |  | Earned Value | Plan Week
Product properties delete function remake | 1 | 0.5 |  | 1 | 1
Images preview in product page realisation and then remake | 7 | 6 | 5 | 7 | 5
Category management | 5 | 5 |  | 5 | 5
Advertisements modal | 5 | 5 |  | 5 | 5
Frontend improvements in many views | 8 | 6 |  | 8 | 8
Product discount functionality | 5 | 6 |  | 5 | 5
Optimistic locking | 4 | 4 |  | 4 | 4
Order History | 2 | 1 |  | 2 | 2
Order Repurchase | 3 | 3 |  | 3 | 3
Order Confirmation | 3 | 3 |  | 3 | 3
Debugging | 5 | 5 |  | 5 | 5