## Week
TSPi Week Summary - Form WEEK
Name | Rokas Jaruševičius |  | Date | 05/11/2018
Team | Gryffindor |  | Instructor | Saulius Ragaišis
Week | 1 |  | Cycle | 3
Weekly Data |  |  | Plan | Actual
Project hours for this week |  |  | 40 | 32.5
Project hours this cycle to date |  |  | 40 | 32.5
Earned value for this week |  |  | 40 | 32.5
Earned value this cycle to date |  |  | 40 | 32.5
Total hours for the tasks completed this phase to date |  |  | 40 | 32.5
Team Member Weekly Data | Team Plan Hours | Team Actual Hours | Team Plan Value | Team Earned Value
Team Leader | 9 | 8.5 | 9 | 9
Development Manager | 9 | 7 | 9 | 8
Planning Manager | 8 | 7 | 8 | 8
Quality/Process Manager | 7 | 5 | 7 | 6
Support Manager | 7 | 5 | 7 | 6
Totals | 40 | 32.5 | 40 | 37
Development Tasks Completed | Plan Hours | Actual Hours | Earned Value | Plan Week
Produktų paieška | 7 | 7 | 7 | 7
Atributų front-end | 6 | 4.5 | 6 | 6
Atributų back-end | 12 | 11.5 | 12 | 12
Order info encryptinimas | 3 | 0 | 0 | 3
Testavimas | 3 | 2 | 3 | 3
Debugginimas | 9 | 7.5 | 9 | 9
| 40 | 32.5 | 37 | 40