## Week
TSPi Week Summary - Form WEEK
Name | Denis Semionov |  |  | Date | 2018-04-05
Team | Gryffindor |  |  | Instructor | Saulius Ragaišis
Week | 3 |  |  | Cycle | 2
Weekly Data |  |  |  | Plan | Actual
Project hours for this week |  |  |  | 50 | 51
Project hours this cycle to date |  |  |  | 130 | 133.5
Earned value for this week |  |  |  | 50 | 51
Earned value this cycle to date |  |  |  | 130 | 133.5
Total hours for the tasks completed this phase to date |  |  |  | 130 | 133.5
Team Member Weekly Data | Team Plan Hours | Team Actual Hours |  | Team Plan Value | Team Earned Value
Team Leader | 10 | 12 |  | 10 | 10
Development Manager | 10 | 12 |  | 10 | 10
Planning Manager | 10 | 9 |  | 10 | 10
Quality/Process Manager | 10 | 9 |  | 10 | 10
Support Manager | 10 | 9 |  | 10 | 10
Totals | 50 | 51 |  | 50 | 50
Development Tasks Completed | Plan Hours | Actual Hours |  | Earned Value | Plan Week
Product properties delete function remake | 1 | 0.5 |  | 1 | 1
Images preview in product page realisation and then remake | 5 | 7 | 5 | 5 | 5
Category management | 6 | 5 |  | 6 | 6
Advertisements modal | 5 | 5 |  | 5 | 5
Frontend improvements in many views | 5 | 7 |  | 5 | 5
Product discount functionality | 5 | 7 |  | 5 | 5
Request logging | 4 | 3.5 |  | 4 | 4
Optimistic locking | 3 | 4 |  | 3 | 3
Order History | 3 | 1 |  | 3 | 3
Order Repurchase | 4 | 3 |  | 4 | 4
Order Confirmation | 4 | 3 |  | 4 | 4
Debugging | 5 | 5 |  | 5 | 5