## Week
TSPi Week Summary - Form WEEK
Name | Rokas Jaruševičius |  | Date | 04/27/2018
Team | Gryffindor |  | Instructor | Saulius Ragaišis
Week | 2 |  | Cycle | 2
Weekly Data |  |  | Plan | Actual
Project hours for this week |  |  | 40 | 45
Project hours this cycle to date |  |  | 80 | 82.5
Earned value for this week |  |  | 40 | 45
Earned value this cycle to date |  |  | 80 | 82.5
Total hours for the tasks completed this phase to date |  |  | 80 | 82.5
Team Member Weekly Data | Team Plan Hours | Team Actual Hours | Team Plan Value | Team Earned Value
Team Leader | 8 | 8 | 8 | 8
Development Manager | 8 | 8 | 8 | 8
Planning Manager | 8 | 12.5 | 8 | 8
Quality/Process Manager | 8 | 8 | 8 | 8
Support Manager | 8 | 8.5 | 8 | 8
Totals | 40 | 45 | 40 | 40
Development Tasks Completed | Plan Hours | Actual Hours | Earned Value | Plan Week
Checkout realizacija | 12 | 12.5 | 12 | 12
Image upload realizacija | 6.5 | 5.5 | 6.5 | 6.5
Pagination realizacija | 6.5 | 5.5 | 6.5 | 6.5
Unit testing | 3 | 6.5 | 3 | 3
Debugging | 12 | 15 | 12 | 12
| 40 | 45 | 40 | 40