## Week
TSPi Week Summary - Form WEEK
Name | Denis Semionov |  |  | Date | 2018-04-05
Team | Gryffindor |  |  | Instructor | Saulius Ragaišis
Week | 3 |  |  | Cycle | 2
Weekly Data |  |  |  | Plan | Actual
Project hours for this week |  |  |  | 40
Project hours this cycle to date |  |  |  | 120 | 82.5
Earned value for this week |  |  |  | 40 | 45
Earned value this cycle to date |  |  |  | 120 | 82.5
Total hours for the tasks completed this phase to date |  |  |  | 80 ???? | 82.5
Team Member Weekly Data | Team Plan Hours | Team Actual Hours |  | Team Plan Value | Team Earned Value
Team Leader
Development Manager | 10 | 15 |  | 10 | 15
Planning Manager
Quality/Process Manager
Support Manager
Totals
Development Tasks Completed | Plan Hours | Actual Hours |  | Earned Value | Plan Week
Lots of bugfixes ?
Product properties delete function remake | 1 | 0.5 |  | 1 | 1
Images preview in product page realisation and then remake | 7 | 6 | 5 | 7 | 5
Category management
Advertisements modal
Frontend improvements in many views | 15 | 6 |  | 7 | 7
Product discount functionality
Optimistic locking
Order repurchase, order confirmation
Debugging