## Week
TSPi Week Summary - Form WEEK
Name | Rokas Jaruševičius |  | Date | 04/13/2018
Team | Gryffindor |  | Instructor | Saulius Ragaišis
Week | 2 |  | Cycle | 1
Weekly Data |  |  | Plan | Actual
Project hours for this week |  |  | 30 | 10
Project hours this cycle to date |  |  | 66 | 34
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 66 | 34
Team Member Weekly Data | Team Plan Hours | Team Actual Hours | Team Plan Value | Team Earned Value
Team Leader
Development Manager | 10 | 10 | 10 | 11
Planning Manager | 8 | 5 | 8 | 8
Quality/Process Manager
Support Manager
0
Totals | 8 | 5
Development Tasks Completed | Plan Hours | Actual Hours | Earned Value | Plan Week
Krepšelio funkcionalumo įgyvendinimas | 10 | 10 | 10 | 10
Duomenų bazės koregavimas | 1 | 2 | ?????? Kiek? -1? XD | 0, nes neplanuota xD
Produkto aprašymo punktų atvaizdavimas | 3 | 3 | 3 | 3
Produkto aprašymo punktų pridėjimas bei trynimas | 7 | 5 | 7 | 7