## Week
TSPi Week Summary - Form WEEK
Name | Rokas Jaruševičius |  | Date | 04/06/2018
Team | Gryffindor |  | Instructor | Saulius Ragaišis
Week | 1 |  | Cycle | 1
Weekly Data |  |  | Plan | Actual
Project hours for this week |  |  | 36 | 24
Project hours this cycle to date |  |  | 36 | 24
Earned value for this week |  |  | 36 | 36
Earned value this cycle to date |  |  | 36 | 36
Total hours for the tasks completed this phase to date |  |  | 36 | 24
Team Member Weekly Data | Team Plan Hours | Team Actual Hours | Team Plan Value | Team Earned Value
Team Leader | 8 | 5 | 8 | 8
Development Manager | 8 | 5 | 8 | 8
Planning Manager | 7 | 5 | 7 | 7
Quality/Process Manager | 7 | 5 | 7 | 7
Support Manager | 6 | 4 | 6 | 6
0
Totals | 36 | 24 | 36 | 36
Development Tasks Completed | Plan Hours | Actual Hours | Earned Value | Plan Week
Laiko suplanavimas | 1 | 0.5 | 1 | 1
Reikalavimų išsiaiškinimas, diskutuojant | 2 | 1 | 2 | 2
Strategijos sukūrimas | 3 | 4.5 | 3 | 3
Projekto rizikų identifikavimas | 1 | 0.5 | 1 | 1
Projekto konfigūracijos sukūrimas | 1 | 0.5 | 1 | 1
Komponentų sąveikos suprojektavimas | 4 | 2.5 | 4 | 4
Database ryšių suprojektavimas | 4 | 2.5 | 4 | 4
Testavimo plano sukūrimas | 3 | 1.5 | 3 | 3
IDE konfigūravimas | 1 | 0.5 | 1 | 1
Projekto inicijavimas | 1 | 0.5 | 1 | 1
Minimalus susipažinimas su frameworku | 5 | 2 | 5 | 5
Minimalūs pasibandymai naudojant fw | 5 | 3.5 | 5 | 5
Front-end minimalus apipavidalinimas | 5 | 4 | 5 | 5