## Week
TSPi Week Summary - Form WEEK
Name | Rokas Jaruševičius |  | Date | 05/25/2018
Team | Gryffindor |  | Instructor | Saulius Ragaišis
Week | 3 |  | Cycle | 3
Weekly Data |  |  | Plan | Actual
Project hours for this week |  |  | 44 | 41.5
Project hours this cycle to date |  |  | 130 | 124.5
Earned value for this week |  |  | 44 | 44
Earned value this cycle to date |  |  | 130 | 124.5
Total hours for the tasks completed this phase to date |  |  | 130 | 124.5
Team Member Weekly Data | Team Plan Hours | Team Actual Hours | Team Plan Value | Team Earned Value
Team Leader | 10 | 9.5 | 10 | 10
Development Manager | 9 | 9.5 | 9 | 9
Planning Manager | 8 | 7 | 8 | 8
Quality/Process Manager | 8 | 7 | 8 | 8
Support Manager | 9 | 8.5 | 9 | 9
Totals | 44 | 41.5 | 44 | 44
Development Tasks Completed | Plan Hours | Actual Hours | Earned Value | Plan Week
Responsive design | 8 | 5.5 | 8 | 8
Front-end improvement | 5 | 3.5 | 5 | 5
Sistemos optimizavimas | 28 | 30 | 28 | 28
Pilnas sistemos ištestavimas | 3 | 2.5 | 3 | 3
| 44 | 41.5 | 44 | 44